## Cover Page
Cover Page
Project Name : Prestashop
Project Link : https://demo.prestashop.com/#/en/front
Start Date: 13-08-2026
Submitted to: Greeshma
Submitted By: Aju Chummar
End Date: 14-09-2026

## Features
Features
SL No | Features | Hyperlinks
1 | Home Page | TEST CASE | RTM
2 | Product Description | TEST CASE | RTM
3 | Contact Us | TEST CASE | RTM
4 | Add to Cart | TEST CASE | RTM
5 | Checkout | TEST CASE | RTM
6 | Customer Login | TEST CASE | RTM
7 | New Customer Login | TEST CASE | RTM
8 | Order Tracking | TEST CASE | RTM
9 | Product Filters | TEST CASE | RTM

## Test Case Execution
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status
Home Page
TC_PRESH_101 | Home Page | Verify homepage loads successfully | Browser is open | 1. Open browser 2. Enter URL for PrestaShop demo 3. Press Enter | https://demo.prestashop.com/#/en/front | Homepage should load without errors | Homepagae loaded | Pass
TC_PRESH_102 | Home Page | Verify page title | Home page is loaded | 1. Check browser tab title | https://demo.prestashop.com/#/en/front | Correct page title should be displayed | Page Title is correct | Pass
TC_PRESH_103 | Home Page | Verify language selector | Home page is loaded | 1. Click language selector | English | Available language options should be displayed | Dropdown worked as expected | Pass
TC_PRESH_104 | Home Page | Change website language | Home page is loaded | 1. Select another language other than English in the drop down menu from language section | Dansk | Store content should change to selected language | Language changed | Pass
TC_PRESH_105 | Home Page | Verify loading products section | Home page is loaded | 1. Check menu has loaded | https://demo.prestashop.com/#/en/front | Menu should be displayed properly | Shown as expected | Pass
TC_PRESH_106 | Home Page | Clicking on a product and checking new URL | Home page is loaded | 1. Open browser 2. Enter URL for PrestaShop demo 3. Select a product 4. click on the product | https://demo.prestashop.com/#/en/front | The product should displayed in the new page with new URL in the browser | product displayed but the url remained same | fail
TC_PRESH_107 | Search | Search for a valid product | Home page is loaded | 1. Enter a valid product name 2. Click search | enter value " t-shirt" | Relevant search results should be displayed with all items available | result displayed correctly | Pass
TC_PRESH_108 | Search | Search using invalid product | Home page is loaded | 1. Enter invalid product name 2. Search | xyz123 | Appropriate no-results message should be displayed | Displayed result with wrong products | fail
TC_PRESH_109 | Responsive | Responsive time | Loading time for website | 1, Open browser 2. enter website address 3. wait for response | https://demo.prestashop.com/#/en/front | The website should load fast and should respond quickly | Website is loading very slowly eventhough the internet spped is good | fail
TC_PRESH_110 | Banner slider button | Visibility of naigation Button Backwards | Home page is loaded | 1. Homepage is loaded 2. Navigate back button visible | https://demo.prestashop.com/#/en/front | Back navigation button should be visible. | Back navigation button is visible | Pass
TC_PRESH_111 | Banner slider button | Visibility of naigation Button Frontwards | Home page is loaded | 1. Homepage is loaded 2. Navigate front button visible | https://demo.prestashop.com/#/en/front | Front navigation button should be visible. | Front navigation button is visible | Pass
TC_PRESH_112 | Banner slider button | Able to click back navigation button | Home page is loaded | 1. Homepage is loaded 2. Navigate back button visible 3. click on the back button | https://demo.prestashop.com/#/en/front | Back navigation button should be visible and able to click | Back navigation button is visible and clcikable | Pass
TC_PRESH_113 | Banner slider button | Able to click front navigation button | Home page is loaded | 1. Homepage is loaded 2. Navigate front button visible 3. click on the front button | https://demo.prestashop.com/#/en/front | Front navigation button should be visible and able to click | Front navigation button is visible and clickable | Pass
TC_PRESH_114 | Image Slider visibility | Visibility of banner | Home page is loaded | 1, Home page is loaded. 2, Scrolldown to banner area 3. banner is loaded , banner 1, banner 2, banner3 | https://demo.prestashop.com/#/en/front | Banners should be visible | banners are visible | Pass
TC_PRESH_115 | Home Page | Visiblity of products in home page | Home page is loaded | 1. Home page is loaded. 2. scroll down to products section | https://demo.prestashop.com/#/en/front | Available discounted /products should display in the homepage | Products are visible | Pass
TC_PRESH_116 | Home Page | Header area display | Home page is loaded | 1) Homepage is loaded 2) Logo is visible | https://demo.prestashop.com/#/en/front | Brand Logo should be visible | logo is displayed | Pass
TC_PRESH_117 | Home Page | Products image display in homepage | Home page is loaded and scrolled to products area | 1) Homepage is loaded 2) scroll down to product area 3) images of the product displayed | https://demo.prestashop.com/#/en/front | Product images should be visible | product images are displayed | Pass
TC_PRESH_118 | Home Page | Products image size in homepage | Home page is loaded and scrolled to products area | 1) Homepage is loaded 2) scroll down to product area 3) images of the product displayed in correct size | https://demo.prestashop.com/#/en/front | Product images should be visible in desired size | product images are displayed in desired size | Pass
TC_PRESH_119 | Home Page | Products prize shown in homepage | Home page is loaded and scrolled to products area | 1) Homepage is loaded 2) scroll down to product area 3) price of the product displayed | https://demo.prestashop.com/#/en/front | Product price should be visible | product price is displayed | Pass
TC_PRESH_120 | Home Page | All featured products button visibility | Home page is loaded and scrolled desired location for button | 1) Homepage is loaded 2) scroll down to desired area for button to displayed 3) verify desired button is displayed | https://demo.prestashop.com/#/en/front | All featured products button should be visible | All featured products button is visible | Pass
TC_PRESH_121 | Home Page | Verify logo navigation | Homepage is loaded | 1. Click the logo | Logo in menubar | User should be navigated to the homepage | User was able to navigated to the homepage | Pass
TC_PRESH_122 | Home Page | Verify the display of product description | Browser with product page open | 1. clcik on product 2. Page loads with details of product | https://demo.prestashop.com/#/en/front | Product page should load without errors | Executed correctly | Pass
Product Description
TC_PRESH_201 | Product page | Verify the displayed product and the origunal image clicked on | Browser with product page open | 1. clcik on product 2. Page loads with details of product 3. Verify the product description with product | https://demo.prestashop.com/#/en/front | Product page should load without errors | Executed correctly | Pass
TC_PRESH_202 | Product page | Verify the display of product Title | Browser with product page open | 1. clcik on product 2. Page loads with details of product 3. Verify the product details with product | https://demo.prestashop.com/#/en/front | The Product details should be displayed correctly | Executed correctly | Pass
TC_PRESH_203 | Product Description | Verify description after browser Back/Forward | Product details page is open | 1. Navigate back 2. Navigate forward | Any product page | Product description should load correctly | Executed correctly | Pass
TC_PRESH_204 | Product Description | Verify description matches selected product | Product list is displayed | 1. Select Product A 2. Open description 3. Note description 4. Return to listing 5. Select Product B | Product A & B | Each product should display its own correct description | Executed correctly | Pass
TC_PRESH_205 | Product Description | Verify description is not blank | Product page is open | 1. Navigate to Description section | Product with description | Description should contain relevant product information | Executed correctly | Pass
TC_PRESH_206 | Product Description | Amount display | Product page is open | 1. Navigate to Description section 2. Verify the display of Price correctly | Product with price details | Page should contain price information | Executed correctly | Pass
TC_PRESH_207 | Product Description | visibility of - ve button to decrese quantity | Product page is open | 1. Navigate to product section 2. the -ve button is available | Product with description and buttons | Button visible | Executed correctly | Pass
TC_PRESH_208 | Product Description | visibility of + ve button to increse quantity | Product page is open | 1. Navigate to product section 2. the -ve button is available | Product with description and buttons | Button visible | Executed correctly | Pass
TC_PRESH_209 | Product Description | Verify product description section is displayed | homepage is loaded | 1. Open the PrestaShop 2. Navigate to any product 3. Open product details | Any available product page | Product description is displayed | Executed correctly | Pass
TC_PRESH_210 | Product Description | Verify description tab is available | Product page is open | 1. Open any product 2. Locate the Description tab | Any available product page | Description tab should be visible | Executed correctly | Pass
TC_PRESH_211 | Product Description | Verify complete product description content | Product page is open | 1. Open a product 2. Click Description 3. Read the displayed content | Existing product page | Complete description should be displayed without missing text | Executed correctly | Pass
TC_PRESH_212 | Product Description | Verify description matches the selected product | Product page is open | 1. Note product name 2. Open Description 3. Verify description content | Selected product | Description should correspond to the selected product | Executed correctly | Pass
TC_PRESH_213 | Product Description | Verify description formatting | Product page is open | 1. Open product 2. Navigate to Description section 3. Check headings, paragraphs, | Formatted description | Formatting should be displayed correctly without broken HTML or layout | Executed correctly | Pass
TC_PRESH_214 | Product Description | Verify description does not overlap other product information | Product page is open | 1. Open product 2. Scroll to Description 3. Check surrounding elements | Any product | Description should not overlap images, price, buttons, or other sections | Executed correctly | Pass
TC_PRESH_215 | Product Description | Verify description on different screen sizes | Product page is accessible | 1. Open product on desktop 2. Resize browser to tablet/mobile dimensions 3. Check Description | Desktop, Mobile | Description should remain readable and properly aligned | Executed correctly | Pass
TC_PRESH_216 | Product Description | Verify imagesinside description | Product description contains media | 1. Open product 2. Navigate to Description 3. Check embedded media | Product with image | Embedded content should load correctly without distortion | Executed correctly | Pass
TC_PRESH_217 | Product Description | Verify description after browser refresh | Product page is open | 1. Open product 2. Navigate to Description 3. Refresh browser | Any product page | Description should remain available and unchanged after refresh | Redirected to homepage | Fail
TC_PRESH_218 | Product Description | Verify description is visible without login | Product page is open | 1. Open website 2. Select a product 3. View Description | Guest user / user not logged in | Description should be accessible without login | Executed correctly | Pass
TC_PRESH_219 | Product Description | Verify description after adding product to cart | Product page is open | 1. View description 2. Add product to cart 3. Return to product page | Any product | Description should remain unchanged | Executed correctly | Pass
TC_PRESH_220 | Product Description | Verify description after navigating back | Product page is open | 1. Open Description 2. Navigate to another page 3. Click browser Back | Any product | Product description should load correctly | Executed correctly | Pass
TC_PRESH_221 | Product Description | Verify special symbols | Product page is open | 1. Open Description 2. Check symbols | Any product page with symbols | Symbols should display correctly | Executed correctly | Pass
TC_PRESH_222 | Product Description | Verify description image size | Product page is open | 1. Open product 2. View Description 3. Inspect image | Product description image | Image should display without distortion or unexpected scaling | Executed correctly | Pass
Contact Us
TC_PRESH_301 | Contact Us | Verify Contact Us form is displayed | Home Page is open | 1. Click in the contact us | https://demo.prestashop.com/#/en/front | Contact Us form should be displayed correctly | Executed correctly | Pass
TC_PRESH_302 | Contact Us | Verify Contact Us page URL | Contact Us page is open | 1. contact us page URL check | https://demo.prestashop.com/#/en/front | Contact us URL should be displayed correctly | Not shown correctly | fail
TC_PRESH_303 | Contact Us | Submit form with empty fields | Contact Us page is open | 1. Enter no values in the fields 2. Press Button "Send your Message" | https://demo.prestashop.com/#/en/front | Should show warning in mandatory fields | Shown warning | Pass
TC_PRESH_304 | Contact Us | Submit form with Valid data | Contact Us page is open | 1. Enter valid values in the fields 2. Press Button "Send your Message" | 1. Select Subject as "Customer Service" 2. Email Address: "1234@a.com " 3. Message: "Hello" 4. Click on "Send your message" button | Should display successful send message."Your message has been successfully sent to our team." | Message sucessfully displayed | Pass
TC_PRESH_305 | Contact Us | Clicking on the email address in contact us page. | Contact Us page is open | 1, Click on the email address in the contact us page. 2. open your email to send information | demo@prestashop.com | Should successfully open customer email for sending email. | Sucessfully opened email | Pass
TC_PRESH_306 | Contact Us | Character limit | Contact Us page is open and user is in Message option | 1. Enter valid values in the Message field | 1. Select Subject as "Customer Service" 2. Email Address: "1234@a.com " 3. Message: character more than 1000 . | should show limit info 1000 | Not shown any limit | fail
TC_PRESH_307 | Contact Us | Selecting Subject | Contact Us page is open | 1. clcik on the drop down menu 2. Selct the next option currently selected | Customer service Webmaster | the option got selected and active | sucessfully selected | Pass
TC_PRESH_308 | Contact Us | Submit form with Valid data with a email address other than .com | Contact Us page is open | 1. Enter valid values in the fields 2. Press Button "Send your Message" | 1. Select Subject as "Webmaster" 2. Email Address: "1234@a.nz " 3. Message: "Newzeland" 4. Click on "Send your message" button | Should display successful send message."Your message has been successfully sent to our team." | Message sucessfully displayed | Pass
TC_PRESH_309 | Contact Us | Verify Message accepts special characters | Contact Us page is open | 1. Select Customer service 2. Enter valid email 3. Enter special characters in Message | Hello! @#$% & Welcome. | Message should accept supported special characters without errors | sucessfully selected | Pass
TC_PRESH_310 | Contact Us | Verify Message field accepts multiline text | Contact Us page is open | 1. Click Message field 2. Enter multiple lines | Line 1 Line 2 Line 3 | Multiline message should be accepted and displayed correctly | sucessfully selected | Pass
TC_PRESH_311 | Contact Us | Verify Send button is available | Contact Us page is open | 1. Navigate to Contact Us page 2. Observe Send button | Send button visibility | Send your message button should be visible and enabled end of form | sucessfully shown | Pass
TC_PRESH_312 | Contact Us | Verify attachment upload if available | Contact Us page is open | 1. Click Choose File 2. Select supported file 3. Submit valid form | Check with PDF/JPG/PNG file | File should be attached and form should submit successfully | sucessfully selected | Pass
TC_PRESH_313 | Contact Us | Verify unsupported attachment format | Contact Us page is open | 1. Click Choose File 2. Select unsupported file 3. Click Send | Unsupported file such as .csv, .exe | Appropriate file-format error should be displayed and submission should be prevented | the file was able to upload | fail
TC_PRESH_314 | Contact Us | Verify Contact Us page | Contact Us page is open | 1. Check Subject changeable 2. Check Email address clickable for write 3. Check Attachment clickable attach 4. Check Message clickable for write 5. Check Send button clickable | Contact us page displayed | All required controls should be properly aligned, visible and usable | successful | Pass
TC_PRESH_315 | Contact Us | Verify page behavior after refresh | Contact Us page is open | 1. Enter data 2. Refresh page | Contact us page displayed | Page should reload without breaking the Contact Us functionality | redirected to home page | fail
TC_PRESH_316 | Contact Us | Verify Contact Us form in different browsers | site is accessible | 1. Open Contact Us in Chrome 2. Repeat in Firefox 3. Repeat in Edge | Contact us page displayed | Contact form should function consistently across supported browsers | successful | Pass
TC_PRESH_317 | Contact Us | Verify entered data is cleared/handled after successful submission | Valid Contact Us form data is entered | 1. Submit valid form 2. Observe form after submission | 1. Select Subject as "Customer Service" 2. Email Address: "1234@a.com " 3. Message: "Hello" 4. Click on "Send your message" button | Success confirmation should appear and form should behave according to the application's post-submission flow | sucessfully shown | Pass
TC_PRESH_318 | Contact Us | Verify form does not submit with blank fields | Contact Us page is open | 1. Leave all fields blank 2. Click Send | Blank fields | Required-field validation should be displayed and form should not be submitted | sucessfully shown error info | Pass
TC_PRESH_319 | Contact Us | Verify Subject/Contact dropdown is displayed | Contact Us page is open | 1. Click Subject dropdown | options in dropdown | Subject dropdown should be displayed with available options | sucessfully selected | Pass
TC_PRESH_320 | Contact Us | Location info | Contact Us page is open | 1, Check the Address is Visible | Countact us page | The location address is visible | visible and able to read | Pass
Add to cart
TC_PRESH_401 | Add to Cart | Verify Add to Cart button is displayed for a product | User is on the PrestaShop product page | 1. Open the website 2. Navigate to any product | Product: Hummingbird Printed T-Shirt | Add to Cart button is displayed and enabled to click | product is added to cart | Pass
TC_PRESH_402 | Add to Cart | Add a single product to the cart | Product is available | 1. Open a product 2. Click Add to Cart | Product: Hummingbird Printed T-Shirt | Product should successfully added to the cart | product was added to cart | Pass
TC_PRESH_403 | Add to Cart | Verify cart count after adding one product | Product is available | 1. Add one product to cart 2. Observe cart icon/count | Quantity: 1 | Cart count should increases to 1 with the product details | count incresed by 1 | Pass
TC_PRESH_404 | Add to Cart | Verify product details in cart | Product has been added | 1. Add product to cart 2. Open the cart | Product: Pack Mug + Framed poster | Correct product name, image, price and quantity should displayed | all displayed as expected | Pass
TC_PRESH_405 | Add to Cart | Add multiple quantities of the same product | Product is available | 1. Add a product to cart 2. Increase quantity using quantity controller | Quantity: 2 or more | Cart should displays the product with quantity 2 and correct total price | updated the details accordingly | Pass
TC_PRESH_406 | Add to Cart | Add different products to the cart | Multiple products are available | 1. Add Product A 2. Return to product listing 3. Add Product B 4. Open cart | Product A + Product B | Both products are displayed in the cart | producsts are added to cart | Pass
TC_PRESH_407 | Add to Cart | Verify cart total after adding a product | Product is available | 1. Note product price 2. Add product to cart 3. Open cart | Product price: displayed product price in page | Cart total matches the product price plus applicable shipping/taxes if any | producst price si displayed correctly in cart | Pass
TC_PRESH_408 | Add to Cart | Verify quantity update in cart | Product is already in cart | 1. Open cart 2. Increase quantity 3. Observe total | Quantity to 2 | Quantity and cart total should updated correctly | Quantity and cart total are updated correctly | Pass
TC_PRESH_409 | Add to Cart | Verify decreasing product quantity | Product is already in cart and quantity is greater than 1 | 1. Open cart 2. Decrease quantity by 1 | Initial quantity in cart 2 | Quantity should decreases to 1 and total is recalculated | Quantity decreases to 1 and total is recalculated | Pass
TC_PRESH_410 | Add to Cart | Remove product from cart | Product is already in cart | 1. Open cart 2. Click Remove/Delete for the product | Product: Hummingbird Printed T-Shirt | Product should removed and cart been updated | product removed | Pass
TC_PRESH_411 | Add to Cart | Verify empty cart after removing the only product | Only one product is in cart | 1. Open cart 2. Remove the product | Quantity: 1 | Cart becomes empty and appropriate empty-cart message is displayed | message dispalyed after removel | Pass
TC_PRESH_412 | Add to Cart | Add product with different size/combination | Product has selectable combinations | 1. Open product 2. Select available size/combination 3. Click Add to Cart | Size: M | Selected product combination is added correctly | size combination was added | Pass
TC_PRESH_413 | Add to Cart | Add product with different color/attribute | Product has selectable attributes | 1. Open product 2. Select a color/attribute 3. Click Add to Cart | Color: Available color | Product with selected attribute is added to cart | colour attribute selected correctly | Pass
TC_PRESH_414 | Add to Cart | Verify Add to Cart confirmation message | Product is available | 1. Open product 2. Click Add to Cart | Any available product | Confirmation message/modal indicates that the product has been successfully added | confirmation message displayed | Pass
TC_PRESH_415 | Add to Cart | Continue shopping after adding product | Product has been added | 1. Click Add to Cart 2. Select Continue Shopping | Any available product | User remains on the shopping/product page and product remains in cart | new product is added | Pass
TC_PRESH_416 | Add to Cart | Proceed to checkout after adding product | Product is in cart | 1. Add product 2. Open cart 3. Click Proceed to checkout | Any available product | Checkout page is opened successfully | checkout page is opened | Pass
TC_PRESH_417 | Add to Cart | Verify cart persists while navigating between pages | Product is in cart | 1. Add product 2. Navigate to another category/page 3. Open cart | Any available product | Previously added product remains in the cart | both product is visible | Pass
TC_PRESH_418 | Add to Cart | Verify cart after page refresh | Product is already in cart | 1. Add product 2. Refresh the page 3. Open cart | Any available product | Cart retains the added product according to the application's session behavior | cart remains same | Pass
TC_PRESH_419 | Add to Cart | Verify cart behavior when adding the same product again | Product is already in cart | 1. Add Product A 2. Return to Product A 3. Click Add to Cart again 4. Open cart | Same product | Application handles duplicate addition correctly according to the configured cart behavior | quantity incresed from 1 to 2 | Pass
TC_PRESH_420 | Add to Cart | Verify cart icon/link opens the cart | Product is already in cart | 1. Add a product 2. Click the cart icon | Any available products | Shopping cart page/summary is displayed | summary is displayed | Pass
TC_PRESH_421 | Add to Cart | Verify cart price calculation for multiple products | Multiple products are available | 1. Add Product A 2. Add Product B 3. Open cart 4. Compare individual prices with total | Product A + Product B | Total is calculated correctly based on selected quantities and prices | total calculated correctly | Pass
TC_PRESH_422 | Add to Cart | Verify Add to Cart functionality using different product categories | Multiple categories are available | 1. Open a category 2. Select a product 3. Add it to cart 4. Repeat for another category | Clothes / Accessories / Art | Products from different categories can be added successfully | various categories added sucessfully | Pass
TC_PRESH_423 | Add to Cart | Verify cart does not contain products | Cart is empty | 1. Add Product A 2. Open cart 3. Verify cart contents | Product A | Only the selected product is present in the cart | details displayed correctly | Pass
TC_PRESH_424 | Add to Cart | Verify Add to Cart functionality after browser navigation | Product is available | 1. Open product 2. Navigate back/forward 3. Click Add to Cart | Any available product | Product is successfully added without UI or functionality errors |  | Pass
TC_PRESH_425 | Add to Cart | checking new URL for cart after adding a product | cart page is loaded | 1. Open a category 2. Select a product 3. Add it to cart | Any available product | The product should displayed in the new page with new URL in the browser | product displayed but the url remained same | fail
TC_PRESH_426 | Add to Cart | Adding products to cart | Product page is open | 1. Open product 2. Add to cart 3. Back to home page 4. Add same product again | Any available product | Number in the cart should increse in the Qty. of the product | the number in Qty was not increased but added as a new product | fail
Check out
TC_PRESH_501 | Check Out | Verify Check Out button is displayed | Product is added to cart | 1. Open PrestaShop front office 2. Add a product to cart 3. Open cart | Product: Hummingbird printed t-shirt | Proceed to checkout / Check Out button is displayed | button displayed | pass
TC_PRESH_502 | Check Out | Verify Check Out button is clickable | Product is available in cart | 1. Open cart 2. Click Proceed to checkout | A product in cart | User is navigated to the checkout process | button clickable | pass
TC_PRESH_503 | Check Out | Verify checkout page loads successfully | Product is added to cart | 1. Open cart 2. Click Proceed to checkout | A product in cart | Checkout page is displayed without errors | added without errors | pass
TC_PRESH_504 | Check Out | Verify product details during checkout | Product is added to cart | 1. Proceed to checkout 2. View cart/order summary | Product name and details | Product image, name, quantity, selected attributes and price are displayed correctly | details displayed correctly | pass
TC_PRESH_505 | Check Out | Verify quantity displayed in checkout | Product is added to cart | 1. Add one product 2. Open checkout | 1 Product and Qty =1 | Correct product quantity should displayed | displayed correctly | pass
TC_PRESH_506 | Check Out | Verify product quantity can be increased | Product is added to cart | 1. Open cart 2. Increase quantity 3. Proceed to checkout | Product Qty incresed to 2 | Updated quantity and product total are displayed correctly | displayed correctly | pass
TC_PRESH_507 | Check Out | Verify product can be removed before checkout | Product is added to cart | 1. Open cart 2. Remove product 3. Proceed to checkout | Product is in cart | Product is removed and checkout cannot proceed with an empty cart | error message shown | pass
TC_PRESH_508 | Check Out | Verify cart total before checkout | Product is added to cart | 1. Open cart 2. Note product price and total 3. Click Proceed to checkout | Product price check | Checkout displays the correct cart total | total was displayed correctly | pass
TC_PRESH_509 | Check Out | Verify Personal Information step | Product is ready for checkout | 1. Proceed to checkout 2. Select guest checkout 3. Enter required information 4. Click Continue | First Name: John Last Name: Eric Email: john@test.com and necessary checkboxs | User proceeds to the Address step | correct info shown | pass
TC_PRESH_510 | Check Out | Verify mandatory personal information validation | Checkout page is displayed | 1. Leave mandatory fields blank 2. Click Continue | Blank required fields | Appropriate validation messages should displayed and user should not able to continue | error message shown | pass
TC_PRESH_511 | Check Out | Verify valid email address | Personal Information step | 1. Enter valid email 2. Complete required fields 3. Click Continue | john@test.com | Email should accepted and user proceeds to next step | validation done shown | pass
TC_PRESH_512 | Check Out | Verify invalid email validation | Personal Information step | 1. Enter invalid email 2. Click Continue | john@ | Validation / Error message should displayed | error message shown | pass
TC_PRESH_513 | Check Out | Verify Address step | Personal information is completed | 1. Complete Personal Information 2. Click Continue | Valid customer details | Address step is displayed | validation done shown | pass
TC_PRESH_514 | Check Out | Verify mandatory address fields | Address step is displayed | 1. Leave required address fields blank 2. Click Continue | Blank fields | Validation/ error messages should displayed | error message shown | pass
TC_PRESH_515 | Check Out | Verify valid address submission | Address step is displayed | 1. Enter valid address details 2. Click Continue | Address: Nickelstreet Zip/Postal Code: 60231 City: Chicago Country: United States | Address is accepted and Shipping Method step is displayed | displayed correctly | pass
TC_PRESH_516 | Check Out | Verify payment step | Shipping method is selected | 1. Click Continue from Shipping Method | Valid checkout data | Payment section is displayed | displayed correctly | pass
TC_PRESH_517 | Check Out | Verify available payment methods | Payment step is displayed | 1. View payment options | Available payment methods | Various configured payment methods are displayed | methords displayed | pass
TC_PRESH_518 | Check Out | Verify payment method selection | Payment step is displayed | 1. Select available payment method | Check banking / other options | Selected payment method is highlighted/accepted | selected displayed correctly | pass
TC_PRESH_519 | Check Out | Verify successful order placement | Valid customer, address, shipping and payment information are available | 1. Complete checkout steps 2. Select payment method 3. Accept terms 4. Click Place Order | Valid checkout data | Order is successfully placed and confirmation page is displayed | message displayed of order sucessfully placed | pass
TC_PRESH_520 | Check Out | Verify order confirmation message | Order is successfully placed | 1. Complete checkout 2. Place order | Valid order | Order confirmation message/page is displayed with order reference | confirmation message displayed | pass
TC_PRESH_521 | Check Out | Verify no duplicate order on repeated Place Order click | All checkout information is completed | 1. Click Place Order 2. Rapidly click Place Order again | Valid checkout data | Only one order is created; duplicate orders are prevented | only executed singletime no duplication | pass
Customer Login
TC_PRESH_601 | Customer Login | Verify Customer Login page is accessible | User is on PrestaShop home page | 1. Open the website 2. Click Sign in | Home page : https://demo.prestashop.com/#/en/front | Login page should be displayed with Email and Password fields, Sign in button and related buttons | page is visible | pass
TC_PRESH_602 | Customer Login | Verify Customer Login page is accessible | Login page is displayed | 1. Enter valid email 2. Enter valid password 3. Click Sign in | Email: pub@prestashop.com Password: 123456789 | Customer should be successfully logged in and redirected to the home/account area | Sign in sucessfully | pass
TC_PRESH_603 | Customer Login | Verify login with invalid email and password | Login page is displayed | 1. Enter invalid email 2. Enter invalid password 3. Click Sign in | Email: wrong@test.com Password: wrong123 | Login should fail and an authentication error message should be displayed | Sign in unsucessful, error message displayed | pass
TC_PRESH_604 | Customer Login | Verify login with valid email and invalid password | Login page is displayed | 1. Enter valid email 2. Enter invalid password 3. Click Sign in | Email: pub@prestashop.com Password: wrong123 | Login should fail and an authentication error should be displayed | Sign in unsucessful, error message displayed | pass
TC_PRESH_605 | Customer Login | Verify login with invalid email and valid password | Login page is displayed | 1. Enter invalid email 2. Enter valid password 3. Click Sign in | Email: wrong@test.com Password: 123456789 | Login should fail and an authentication error should be displayed | Sign in unsucessful, error message displayed | pass
TC_PRESH_606 | Customer Login | Verify login with both fields blank | Login page is displayed | 1. Leave Email blank 2. Leave Password blank 3. Click Sign in | Email: Blank Password: Blank | Validation messages should be displayed and user should not be logged in | Sign in unsucessful, error message displayed | pass
TC_PRESH_607 | Customer Login | Verify login with blank email | Login page is displayed | 1. Leave Email blank 2. Enter password 3. Click Sign in | Email: Blank Password: 123456789 | Email validation message should be displayed and login should not occur | Sign in unsucessful, error message displayed | pass
TC_PRESH_608 | Customer Login | Verify login with blank password | Login page is displayed | 1. Enter valid email 2. Leave Password blank 3. Click Sign in | Email: pub@prestashop.com Password: Blank | Password validation message should be displayed and login should not occur | Sign in unsucessful, error message displayed | pass
TC_PRESH_609 | Customer Login | Verify invalid email format validation | Login page is displayed | 1. Enter an invalid email format 2. Enter password 3. Click Sign in | Email: 1234@ Password: 123456789 | Email validation should be displayed and login should not occur | Sign in unsucessful, error message displayed | pass
TC_PRESH_610 | Customer Login | Verify password masking | Login page is displayed | 1. Click Password field 2. Enter password | Password: 123456789 | Password should be masked by default | Masked sucessfully | pass
TC_PRESH_611 | Customer Login | Verify Show Password functionality | Login page is displayed | 1. Enter password 2. Click password visibility control | Password: 123456789 | Entered password should become visible when Show is selected | Visibility successful | pass
TC_PRESH_612 | Customer Login | Verify email field accepts valid email | Login page is displayed | 1. Click Email field 2. Enter valid email | customer@test.com | Email should be accepted and displayed correctly | Valid email accepted sucessfully | pass
TC_PRESH_613 | Customer Login | Verify Forgot Password link | Login page is displayed | 1. Click Forgot your password | Forget password button | Password recovery page form should be displayed | page displayed sucessfully after click | pass
TC_PRESH_614 | Customer Login | Verify Create Account link | Login page is displayed | 1. Click on Create your account | create account button | Customer registration page should be displayed | page displayed sucessfully after click | pass
TC_PRESH_615 | Customer Login | Verify successful login maintains customer session | Customer has valid credentials | 1. Login using valid credentials 2. Navigate to another page 3. Return to home page | pub@prestashop.com 123456789 | Customer should remain logged in and customer account/name should be displayed while navigating in various pages | login page was stable in various pages | pass
TC_PRESH_616 | Customer Login | Verify customer logout | Customer is logged in | 1. Click Sign out | Valid logged-in session | Customer should be logged out and home page should be displayed | logged out and homepage displayed | pass
TC_PRESH_617 | Customer Login | Verify login after logout | Customer has logged out | 1. Click Sign in 2. Enter valid credentials 3. Click Sign in | pub@prestashop.com 123456789 | Customer should be able to log in again successfully | was able to relogin immediately after the log out | pass
TC_PRESH_618 | Customer Login | Verify login page elements | Login page is displayed | 1. Display of Email field 2. Display of Password field 3. Display ofSign in button 4. Display of Forgot Password and Create Account links | Sign in page | All required login controls should be visible, properly aligned and usable | the control items are displayed correctly | pass
TC_PRESH_619 | Customer Login | Verify email field accepts uppercase characters | Login page is displayed | 1. Enter uppercase version of valid email 2. Enter valid password 3. Click Sign in | PUB@PRESTASHOP.COM | Application should handle email case according to email validation rules | Email case accepted | pass
TC_PRESH_620 | Customer Login | Verify email without @ symbol | Login page is displayed | 1. Enter email without @ 2. Enter password 3. Click Sign in | customertest.com | Email validation should fail | error message displayed | pass
TC_PRESH_621 | Customer Login | Invalid email to Forgot your password section | Forgetpassword Page displayed | 1. Enter email without @ 2. Click Send rest link | customertest.com | Email validation should fail | error message displayed | pass
TC_PRESH_622 | Customer Login | Invalid email to Forgot your password section | Forgetpassword Page displayed | 1. Enter email without . 2. Click Send rest link | customertest@com | Email validation should fail | error message displayed | pass
New Customer Login
TC_PRESH_701 | New Customer Login | Verify New Customer/Login page loads successfully | PrestaShop demo site is accessible | 1. Open PrestaShop demo 2. Click Sign in | URL: https://demo.prestashop.com/#/en/front | Login/authentication page is displayed with options for existing customers and new customers | Site was accessable | pass
TC_PRESH_702 | New Customer Login | Verify new customer registration section is displayed | Login page is open | 1. Locate Create Your Account | search Create account button | New customer registration option is visible and clickable | Button was visible and clickable | pass
TC_PRESH_703 | New Customer Login | Verify registration page with First name | Registration page is open | 1. Enter a First Name 2. Continue | First Name : Raven | Customer should be able to Enter first Name | Was able to enter Firstname | pass
TC_PRESH_704 | New Customer Login | Verify registration page with Last name | Registration page is open | 1. Enter a Last Name 2. Continue | Last Name :John | Customer should be able to Enter Last Name | Was able to enter Last Name | pass
TC_PRESH_705 | New Customer Login | Verify registration with valid email address | Registration page is open | 1. Enter a valid email 2. Continue | Email: newcustomer01@example.com | Customer should able to enter valid email for registration | Customer was able to enter email | pass
TC_PRESH_706 | New Customer Login | Verify registration with invalid email format | Registration page is open | 1. Enter invalid email 2. Continue | Email: newcustomer01@ | Validation message is displayed and user cannot continue | Error message displayed | pass
TC_PRESH_707 | New Customer Login | Verify registration with blank email | Registration page is open | 1. Leave email blank 2. Click Continue | Email: Blank | Required-field validation should be displayed | Required / filed missing info shown | pass
TC_PRESH_708 | New Customer Login | Verify duplicate email registration | A customer account already exists with the test email | 1. Enter an existing email 2. Continue | Email: Existing registered email | System prevents duplicate registration and displays an appropriate message | System displays error message preventing duplication | pass
TC_PRESH_709 | New Customer Login | Verify mandatory personal information fields | Registration form is open | 1. Leave mandatory fields blank 2. Click Create Account | Mandatory fields: Blank | Validation messages are displayed for each required field | Required / filed missing info shown | pass
TC_PRESH_710 | New Customer Login | Verify new customer registration with valid data | Registration form is open | 1. Enter valid personal details 2. Enter valid password 3. Accept required terms if displayed 4. Click create Account | First Name: Aju Last Name: Kumar Email: newcustomer02@example.com Password: Test@123451 | Account should created successfully and customer is logged in or redirected to the account confirmation/account page | account created sucessfully | pass
TC_PRESH_711 | New Customer Login | Verify password field masking | Registration form is open | 1. Click password field 2. Type password | Password: Test@123451 | Password characters should be masked | password was masked as per requirement | pass
TC_PRESH_712 | New Customer Login | Verify weak/invalid password handling | Registration form is open | 1. Enter a password that does not meet the site's rules 2. Submit form | Password: 123 | System should display password validation feedback and prevents registration | Error message displayed | pass
TC_PRESH_713 | New Customer Login | Verify successful login using newly created customer account | New customer account has been created | 1. Log out if already logged in 2. Open Sign in 3. Enter registered email and password 4. Click Sign in | Email: newcustomer02@example.com Password: Test@1234567892 | Customer should successfully authenticated and account/customer name should displayed | sucessfully reloged | pass
TC_PRESH_714 | New Customer Login | Verify login with incorrect password | A customer account exists | 1. Open Sign in 2. Enter valid email and incorrect password 3. Click Sign in | Email: newcustomer02@example.com Password: Wrong@123 | Login fails and an appropriate authentication error should displayed | Authentication failed message displayed | pass
TC_PRESH_715 | New Customer Login | Verify login with unregistered email | Login page is open | 1. Enter an unregistered email 2. Enter any password 3. Click Sign in | Email: unknowncustomer@example.com Password: Test@1234545645855 | Login fails and an appropriate authentication error should displayed | Authentication failed message displayed | pass
TC_PRESH_716 | New Customer Login | Verify login with blank email and password | Login page is open | 1. Leave email blank 2. Leave password blank 3. Click Sign in | Email: Blank Password: Blank | Required-field validation should displayed and login is not performed | Authentication failed message displayed | pass
TC_PRESH_717 | New Customer Login | Verify email field accepts valid email format | Login page is open | 1. Enter a valid email format 2. Move focus to another field | Email: customer@example.com | Email should accepted without format validation error | accepted the email | pass
TC_PRESH_718 | New Customer Login | Verify logout after successful new customer login | Customer is successfully logged in | 1. Click Sign out / Log out | Sign out button | Customer session ends and login option is displayed again | Sucessfully logged out | pass
TC_PRESH_719 | New Customer Login | Verify protected account access after logout | Customer has logged out | 1. Click Account icon, near Sign In | account icon visibility | User should redirected to login/authentication page instead of accessing the protected account directly | Displayed the login in page | pass
TC_PRESH_720 | New Customer Login | Verify login page works after browser refresh | Login page is open | 1. Refresh browser 2. Observe page | refresh page, in login page | Login/registration pageshould reloads correctly without UI errors | Stayed in login page | pass
TC_PRESH_721 | New Customer Login | Verify login using leading/trailing spaces in email | A customer account exists | 1. Enter email with accidental spaces 2. Enter valid password 3. Click Sign in | Email: newcustomer02@example.com Password: Wrong@123 | System trims spaces before input with appropriate validation; it must not authenticate an unintended account | Trims spaces before email and accepts the email with valid info | pass
TC_PRESH_722 | New Customer Login | Verify multiple failed login attempts are handled safely | A customer account exists | 1. Enter incorrect password repeatedly 2. Observe responses | Email: newcustomer02@example.com Password: Wrong@123 | Authentication remains secure and appropriate error should shown according to configuration | Authentication failed message displayed | pass
TC_PRESH_723 | New Customer Login | Customer Date of Birth | Sign up form | 1. Sign in 2. Create your account 3. Enter informations. 4, In date column enter a future date 5, Click on create account | 12-05-2030 | the column should not accept the future date | Future date was accepted | Fail
Order Tracking
TC_PRESH_801 | Order Tracking | Verify Order Tracking page is accessible | PrestaShop demo site is loaded | 1. Open demo site 2. Scroll to footer 3. Click 'Order tracking' | page scrolling + locate footer | Order Tracking page should open successfully. | Order tracking page was opened sucessfully | Pass
TC_PRESH_802 | Order Tracking | Verify Order Reference field is displayed | Order Tracking page is open | 1. Locate Order Reference field 2. Check label, textbox and visibility | footer checking | Order Reference field should visible and usable. | Order reference input is visible | Pass
TC_PRESH_803 | Order Tracking | Verify Email Address field is displayed | Order Tracking page is open | 1. Locate Email Address field 2. Check label and textbox | finding input fields | Email Address field should visible and usable. | Email Address input is visible | Pass
TC_PRESH_804 | Order Tracking | Verify Send button is displayed | Order Tracking page is open | 1. Locate Send button 2. Verify it is enabled/available | finding send button | Send button should displayed and available for submission. | Send button is visible and clickable | Pass
TC_PRESH_805 | Order Tracking | Submit tracking form with both fields blank | Order Tracking page is open | 1. Leave Order Reference blank 2. Leave Email Address blank 3. Click Send | Blank Order Reference; Blank Email | Validation message should display and request is not submitted. | No error message displayed | Fail
TC_PRESH_806 | Order Tracking | Submit form with blank Order Reference | Order Tracking page is open | 1. Leave Order Reference blank 2. Enter a valid email 3. Click Send | Email: pub@prestashop.com | Validation message indicates Order Reference is required. | Error message displayed "Please provide the required information" | Fail
TC_PRESH_807 | Order Tracking | Submit form with blank Email Address | Order Tracking page is open | 1. Enter an order reference 2. Leave Email Address blank 3. Click Send | Order Reference: XKBKNABJK | Validation message indicates Email Address is required. | Error message displayed "Please provide the required information" | Fail
TC_PRESH_808 | Order Tracking | Validate invalid email format | Order Tracking page is open | 1. Enter a valid order reference 2. Enter invalid email 3. Click Send | Order Reference: XKBKNABJK Email: test@ | Email validation message is displayed and form is not submitted. | Error message displayed for email | Pass
TC_PRESH_809 | Order Tracking | Track order using invalid Order Reference | Order Tracking page is open | 1. Enter a invalid order reference 2. Enter a valid email 3. Click Send | Order Reference: INVALID999; Email: pub@prestashop.com | User receives a clear message that the order cannot be found or details are invalid. | Error message displayed as per requirement "We couldn't find your order with the information provided, please try again | Pass
TC_PRESH_810 | Order Tracking | Verify incorrect email with valid Order Reference | A valid order exists | 1. Enter valid Order Reference 2. Enter unrelated/incorrect email 3. Click Send | Valid order reference: XKBKNABJK Email: wrong@example.com | Tracking is rejected and a suitable validation/error message is displayed. | Error message displayed as per requirement "We couldn't find your order with the information provided, please try again | Pass
TC_PRESH_811 | Order Tracking | Track order using valid Order Reference and Email | A valid order exists for the supplied customer email | 1. Enter valid Order Reference 2. Enter associated email 3. Click Send | Order Reference: 'XKBKNABJK' Valid email : pub@prestashop.com | Correct order tracking/details page should displayed. | Order tracking page displayed with necessary informations | Pass
TC_PRESH_812 | Order Tracking | Verify order status is displayed for a valid tracked order | Valid order tracking result is available | 1. Track a valid order 2. Inspect order status | Valid order reference and email | Current order status should displayed clearly. | Order status displayed and latest info displyed | Pass
TC_PRESH_813 | Order Tracking | Verify spaces around input values are handled correctly | Order Tracking page is open | 1. Enter reference with leading/trailing spaces 2. Enter valid email 3. Click Send | Order Reference: ' XKBKNABJK ' Valid email : pub@prestashop.com | Application should provide a clear validation message. | Error message displayed as per requirement "We couldn't find your order with the information provided, please try again | Pass
TC_PRESH_814 | Order Tracking | Verify special characters in Order Reference | Order Tracking page is open | 1. Enter special characters in Order Reference 2. Enter valid email 3. Click Send | Order Reference: @@@###; Valid email : pub@prestashop.com | Application should provide a clear validation message. | Error message displayed as per requirement "We couldn't find your order with the information provided, please try again | Pass
TC_PRESH_815 | Order Tracking | Character limt in Order Reference input | Order Tracking page is open | 1. Enter more than 30 characters in Order Reference 2. Enter valid email 3. Click Send | Order Reference: @@@###; Valid email : pub@prestashop.com | Application should stop by 20characters as a maximum limit, if exeed error message should display | Character above 20 has excepted no error message displayed | Fail
TC_PRESH_816 | Order Tracking | Verify browser refresh on Order Tracking page | Order Tracking page is open | 1. Refresh page 2. Verify fields and controls | refresh page / press F5 | Page reloads without errors and Order Tracking form remains functional. | Order page crashes and redirected to homepage | Fail
TC_PRESH_817 | Order Tracking | Verify Order Tracking form is usable on desktop browser | Supported desktop browser is available | 1. Open Order Tracking page 2. Check alignment and controls 3. Enter sample data | Sample valid tracking data page | All labels, fields and button are visible, aligned and usable. | Page and the items are adjusting to size accordingly | Pass
TC_PRESH_818 | Order Tracking | Verify no sensitive order information is shown for invalid details | Order Tracking page is open | 1. Enter invalid reference/email combination 2. Click Send | Order Reference: OHSATSERP Email: test@ | No related customer or order information should display | No information displayed | Pass
TC_PRESH_819 | Order Tracking | Verify repeated invalid submissions do not break the page | Order Tracking page is open | 1. Submit invalid details repeatedly 2. Observe page after each attempt | Order Reference: XKBKNABJK Email: test@ | Appropriate validation remains consistent and the page stays responsive. | Page remains same and responds as per invalid information | Pass
TC_PRESH_820 | Order Tracking | Verify the working of a Reorder Button inside a order | Inside a valid order | 1, Look for Reorder Button. 2. Click on the Button | reorder button location | Should redirect to the shopping cart page and the item should display in Shopping cart | Redirected to Shopping cart but item is missing | Fail
TC_PRESH_821 | Order Tracking | Display of Shipment tracking details | Inside a valid order | 1, Look for Shipment tracking details 2. Look all details Date Carrier Weight Shipping cost Tracking number | Display of tracking numbers | the detail list of shipment should display | Details displayed | Pass
Product Filters
TC_PRESH_901 | Product Filters | Verify filter panel is displayed | User is on a category/product listing page | 1.Open the store 2. Navigate to a category with multiple products 3. Locate Filter by section | a Page of product with multiple products | Filter by panel is visible with filter options | Filter panel displayed | pass
TC_PRESH_902 | Product Filters | Filter products by category/subcategory | User is on a product listing page with category filters | 1.Open Filter by Availability | Available category /subcategory (In stock) | Product list should update with selected category list | product list update accordinly | pass
TC_PRESH_903 | Product Filters | Filter products by size | User is on a listing page where size filter is available | 1. Open size filter 2. Select one size | Available size such as S/M/L | Only products having the selected size should displayed | product list update accordinly | pass
TC_PRESH_904 | Product Filters | Filter products by color | User is on a listing page where color filter is available | 1.Open color filter 2. select one color | Available color | Only products matching the selected color should displayed | product list update accordinly | pass
TC_PRESH_905 | Product Filters | Filter products by brand/manufacturer | User is on a listing page where brand filter is available | 1. Open brand filter 2. select one brand | Available brand | Only products belonging to the selected brand should displayed | product list update accordinly | pass
TC_PRESH_906 | Product Filters | Filter products by price range | User is on a listing page with price filter | 1 .Move/set the price range to a valid range | Valid minimum and maximum price | Only products within the selected price range should displayed | product list update accordinly | pass
TC_PRESH_907 | Product Filters | Apply multiple filters together | Multiple filters are available | 1. Select one color 2. Select one size | Color + size combination | Results should applicable selected filter conditions | product list update accordinly | pass
TC_PRESH_908 | Product Filters | Select multiple values within the same filter | A checkbox-style filter has multiple values | 1. Select two available values in the same filter | Two available colors | Results should contain products matching the selected values according to filter logic | product list update accordinly | pass
TC_PRESH_909 | Product Filters | Clear a selected filter | At least one filter is applied | 1. Select a filter 2. use clear option | Any selected filter | Selected filter sould removed and product results refresh accordingly | product list refreshed after removel of filter | pass
TC_PRESH_910 | Product Filters | Clear all applied filters | Multiple filters are applied | 1.Apply two or more filters 2. click Clear all filters option | Two or more filters | All filters should reset and the original product listing is restored | product list update accordinly | pass
TC_PRESH_911 | Product Filters | Verify result count after filtering | A filter with matching products is available | 1.Apply a filter 2. observe result count | Any valid filter | Displayed result count should change to match the filtered product set | product list update accordinly | pass
TC_PRESH_912 | Product Filters | Verify zero-result filtering | A combination with no matching products can be selected | 1. Apply a restrictive filter combination | Combination expected to return no products | No products message should displayed and page remains stable | page remain stable | pass
TC_PRESH_913 | Product Filters | Verify filter state after browser refresh | At least one filter is applied | 1. Apply a filter 2. refresh the page | Any valid filter | Page should remain in filtered page and the filer should be same | page changed to home page | fail
TC_PRESH_914 | Product Filters | Verify filter with pagination | Filtered results span multiple pages | 1.Apply a filter 2. navigate to next/previous page | Filter with multiple matching products | Pagination should contains only filtered results and navigation works correctly | Multiple pages displayed | pass
TC_PRESH_915 | Product Filters | Verify filter with product sorting | Filtered results are available | 1. Apply a filter 2. change sorting option such as price/name | Valid filter + available sort option | Page should display information accordingly | Filter and option change worked | pass
TC_PRESH_916 | Product Filters | Verify filter after navigating back | A filter has been applied and a product opened | 1. Apply a filter 2. open a product 3. click browser Back | Valid filter + product | Filtered listing should restored correctly or resets consistently according to application behavior | page remained unchanged | pass
TC_PRESH_917 | Product Filters | Verify unavailable filter values are handled correctly | Some filter values may have no matching products | 1. Select an available filter value 2. inspect other filter values after first filter | Available filter value | Unavailable values sould be hidden or handled without producing incorrect results | Unavailable get hidden and only necessary items displayed | pass
TC_PRESH_918 | Product Filters | Verify filter controls are usable | Filter panel is visible | 1. Click each available filter control and interact with it | Mouse/keyboard interaction | Controls respond correctly without overlap, broken UI, or accidental selections | filters displayed correctly and no overlapping | pass
TC_PRESH_919 | Product Filters | Verify filtering does not create broken product links | Filtered products are displayed | 1, Apply a filter 2. click a displayed product | Valid filter displays a product | Selected product should opens its correct product detail page and no broken link occurs | products are displayed correctly | pass

## RTM
REQUIREMENT | REQUIREMENT ID | TEST CASE ID | STATUS
Home Page | PRESH_REQ_1 | TC_PRESH_101 | Pass
|  | TC_PRESH_102 | Pass
|  | TC_PRESH_103 | Pass
|  | TC_PRESH_104 | Pass
|  | TC_PRESH_105 | Pass
|  | TC_PRESH_106 | fail
|  | TC_PRESH_107 | Pass
|  | TC_PRESH_108 | fail
|  | TC_PRESH_109 | fail
|  | TC_PRESH_110 | Pass
|  | TC_PRESH_111 | Pass
|  | TC_PRESH_112 | Pass
|  | TC_PRESH_113 | Pass
|  | TC_PRESH_114 | Pass
|  | TC_PRESH_115 | Pass
|  | TC_PRESH_116 | Pass
|  | TC_PRESH_117 | Pass
|  | TC_PRESH_118 | Pass
|  | TC_PRESH_119 | Pass
|  | TC_PRESH_120 | Pass
|  | TC_PRESH_121 | Pass
|  | TC_PRESH_122 | Pass
Product Description | PRESH_REQ_2 | TC_PRESH_201 | Pass
|  | TC_PRESH_202 | Pass
|  | TC_PRESH_203 | Pass
|  | TC_PRESH_204 | Pass
|  | TC_PRESH_205 | Pass
|  | TC_PRESH_206 | Pass
|  | TC_PRESH_207 | Pass
|  | TC_PRESH_208 | Pass
|  | TC_PRESH_209 | Pass
|  | TC_PRESH_210 | Pass
|  | TC_PRESH_211 | Pass
|  | TC_PRESH_212 | Pass
|  | TC_PRESH_213 | Pass
|  | TC_PRESH_214 | Pass
|  | TC_PRESH_215 | Pass
|  | TC_PRESH_216 | Pass
|  | TC_PRESH_217 | Fail
|  | TC_PRESH_218 | Pass
|  | TC_PRESH_219 | Pass
|  | TC_PRESH_220 | Pass
|  | TC_PRESH_221 | Pass
|  | TC_PRESH_222 | Pass
Contact Us | PRESH_REQ_3 | TC_PRESH_301 | Pass
|  | TC_PRESH_302 | fail
|  | TC_PRESH_303 | Pass
|  | TC_PRESH_304 | Pass
|  | TC_PRESH_305 | Pass
|  | TC_PRESH_306 | fail
|  | TC_PRESH_307 | Pass
|  | TC_PRESH_308 | Pass
|  | TC_PRESH_309 | Pass
|  | TC_PRESH_310 | Pass
|  | TC_PRESH_311 | Pass
|  | TC_PRESH_312 | Pass
|  | TC_PRESH_313 | fail
|  | TC_PRESH_314 | Pass
|  | TC_PRESH_315 | fail
|  | TC_PRESH_316 | Pass
|  | TC_PRESH_317 | Pass
|  | TC_PRESH_318 | Pass
|  | TC_PRESH_319 | Pass
|  | TC_PRESH_320 | Pass
Add to Cart | PRESH_REQ_4 | TC_PRESH_401 | Pass
|  | TC_PRESH_402 | Pass
|  | TC_PRESH_403 | Pass
|  | TC_PRESH_404 | Pass
|  | TC_PRESH_405 | Pass
|  | TC_PRESH_406 | Pass
|  | TC_PRESH_407 | Pass
|  | TC_PRESH_408 | Pass
|  | TC_PRESH_409 | Pass
|  | TC_PRESH_410 | Pass
|  | TC_PRESH_411 | Pass
|  | TC_PRESH_412 | Pass
|  | TC_PRESH_413 | Pass
|  | TC_PRESH_414 | Pass
|  | TC_PRESH_415 | Pass
|  | TC_PRESH_416 | Pass
|  | TC_PRESH_417 | Pass
|  | TC_PRESH_418 | Pass
|  | TC_PRESH_419 | Pass
|  | TC_PRESH_420 | Pass
|  | TC_PRESH_421 | Pass
|  | TC_PRESH_422 | Pass
|  | TC_PRESH_423 | Pass
|  | TC_PRESH_424 | Pass
|  | TC_PRESH_425 | fail
|  | TC_PRESH_426 | fail
Checkout | PRESH_REQ_5 | TC_PRESH_501 | pass
|  | TC_PRESH_502 | pass
|  | TC_PRESH_503 | pass
|  | TC_PRESH_504 | pass
|  | TC_PRESH_505 | pass
|  | TC_PRESH_506 | pass
|  | TC_PRESH_507 | pass
|  | TC_PRESH_508 | pass
|  | TC_PRESH_509 | pass
|  | TC_PRESH_510 | pass
|  | TC_PRESH_511 | pass
|  | TC_PRESH_512 | pass
|  | TC_PRESH_513 | pass
|  | TC_PRESH_514 | pass
|  | TC_PRESH_515 | pass
|  | TC_PRESH_516 | pass
|  | TC_PRESH_517 | pass
|  | TC_PRESH_518 | pass
|  | TC_PRESH_519 | pass
|  | TC_PRESH_520 | pass
|  | TC_PRESH_521 | pass
Customer Login | PRESH_REQ_6 | TC_PRESH_601 | pass
|  | TC_PRESH_602 | pass
|  | TC_PRESH_603 | pass
|  | TC_PRESH_604 | pass
|  | TC_PRESH_605 | pass
|  | TC_PRESH_606 | pass
|  | TC_PRESH_607 | pass
|  | TC_PRESH_608 | pass
|  | TC_PRESH_609 | pass
|  | TC_PRESH_610 | pass
|  | TC_PRESH_611 | pass
|  | TC_PRESH_612 | pass
|  | TC_PRESH_613 | pass
|  | TC_PRESH_614 | pass
|  | TC_PRESH_615 | pass
|  | TC_PRESH_616 | pass
|  | TC_PRESH_617 | pass
|  | TC_PRESH_618 | pass
|  | TC_PRESH_619 | pass
|  | TC_PRESH_620 | pass
|  | TC_PRESH_621 | pass
|  | TC_PRESH_622 | pass
New Customer Loign | PRESH_REQ_7 | TC_PRESH_701 | pass
|  | TC_PRESH_702 | pass
|  | TC_PRESH_703 | pass
|  | TC_PRESH_704 | pass
|  | TC_PRESH_705 | pass
|  | TC_PRESH_706 | pass
|  | TC_PRESH_707 | pass
|  | TC_PRESH_708 | pass
|  | TC_PRESH_709 | pass
|  | TC_PRESH_710 | pass
|  | TC_PRESH_711 | pass
|  | TC_PRESH_712 | pass
|  | TC_PRESH_713 | pass
|  | TC_PRESH_714 | pass
|  | TC_PRESH_715 | pass
|  | TC_PRESH_716 | pass
|  | TC_PRESH_717 | pass
|  | TC_PRESH_718 | pass
|  | TC_PRESH_719 | pass
|  | TC_PRESH_720 | pass
|  | TC_PRESH_721 | pass
|  | TC_PRESH_722 | pass
|  | TC_PRESH_723 | Fail
Order Tracking | PRESH_REQ_8 | TC_PRESH_801 | pass
|  | TC_PRESH_802 | pass
|  | TC_PRESH_803 | pass
|  | TC_PRESH_804 | pass
|  | TC_PRESH_805 | Fail
|  | TC_PRESH_806 | Fail
|  | TC_PRESH_807 | Fail
|  | TC_PRESH_808 | pass
|  | TC_PRESH_809 | pass
|  | TC_PRESH_810 | pass
|  | TC_PRESH_811 | pass
|  | TC_PRESH_812 | pass
|  | TC_PRESH_813 | pass
|  | TC_PRESH_814 | pass
|  | TC_PRESH_815 | Fail
|  | TC_PRESH_816 | Fail
|  | TC_PRESH_817 | pass
|  | TC_PRESH_818 | pass
|  | TC_PRESH_819 | pass
|  | TC_PRESH_820 | Fail
|  | TC_PRESH_821 | pass
Product Filters | PRESH_REQ_9 | TC_PRESH_901 | pass
|  | TC_PRESH_902 | pass
|  | TC_PRESH_903 | pass
|  | TC_PRESH_904 | pass
|  | TC_PRESH_905 | pass
|  | TC_PRESH_906 | pass
|  | TC_PRESH_907 | pass
|  | TC_PRESH_908 | pass
|  | TC_PRESH_909 | pass
|  | TC_PRESH_910 | pass
|  | TC_PRESH_911 | pass
|  | TC_PRESH_912 | pass
|  | TC_PRESH_913 | Fail
|  | TC_PRESH_914 | pass
|  | TC_PRESH_915 | pass
|  | TC_PRESH_916 | pass
|  | TC_PRESH_917 | pass
|  | TC_PRESH_918 | pass
|  | TC_PRESH_919 | pass

## Bug Report
DEFECT ID | Module | Summary | Description | Re-Creation Steps | Expected Result | Actual Result | Severity | Priority | Status
DEFECT_01 | Homepage | URL availability | Most of the time the url of the website is not accessable | https://demo.prestashop.com/#/en/front | The website should up all time | Link missing or site not availabe messages comes when try to acess the website | critical | high | Open
DEFECT_02 | Homepage | Change website language from one language to another | The language is not getting changed in the website after chosing different language. It is a critical issue as the website is used with people around the world | 1. Select another language other than English in the drop down menu from language section | The website languae and details should change from english to selected language | The language remained the same | critical | high | Open
DEFECT_03 | Homepage | Clicking on a product and checking new URL | Clicking on a product and checking new URL as website normal works | 1. Open browser 2. Enter URL for PrestaShop demo 3. Select a product 4. click on the product | The website URL should change to a new URL according to product selected | the URL remained same as original | critical | high | Open
DEFECT_04 | Contact Us | Verify Contact Us page URL | The URL in the page should change in browser but nothing changed and remaind same | https://demo.prestashop.com/#/en/front | The URL in the page should change in browser | the URL remaind the same | critical | high | Open
DEFECT_05 | Contact Us | Character limit is not set | In the message option there should be a limit for the characters. But in the input area the limit was not set. | 1. Select Subject as "Customer Service" 2. Email Address: "1234@a.com " 3. Message: character more than 1000 . | after reaching 1000 user shouldnot able to input values | the character limit was not set and it is going beyond 1000 | major | medium | Open
DEFECT_06 | Product Description | Verify description after browser refresh | Product page is open | 1. Open product 2. Navigate to Description 3. Refresh browser | Description should remain available and unchanged after refresh | went to homepage | major | high | Open
DEFECT_07 | Contact Us | Verify page behavior after refresh. | Contact Us page is open and after doing the refresh, the page should remain in contact us page only | 1. Enter data 2. Refresh page | Page should reload without breaking the Contact Us functionality | redirected to home page | major | high | Open
DEFECT_08 | Cart | Adding products | while adding products to cart, it is not getting add to the previous same items. It shows as a separate item | 1. Open product 2. Add to cart 3. Back to home page 4. Add same product again | Number in the cart should increse in the Qty. of the product | the number in Qty was not increased but added as a new product | major | medium | Open
DEFECT_09 | New cusomer login | Accepting dates | in new user creation the input for DOB accepts future date | 1. Sign in 2. Create your account 3. Enter informations. 4, In date column enter a future date : 12-05-2030 5, Click on create account | the column should not accept the future date | Future date was accepted | critical | high | Open
DEFECT_10 | Order Tracking | Submit tracking form with Order Reference & Email fields blank | Submit tracking form with Order Reference & Email fields blank, this should trigger error message to user to enter data to the fields | 1. Leave Order Reference blank 2. Leave Email Address blank 3. Click Send | Validation message should display and request is not submitted. | No error message displayed | minor | medium | Open
DEFECT_11 | Order Tracking | Submit form with blank Order Reference | Submit form with blank Order Reference and it should indicate the error message towards Order reference missing | 1. Leave Order Reference blank 2. Enter a valid email : pub@prestashop.com 3. Click Send | Validation message indicates Order Reference is required. | Error message displayed "Please provide the required information" | minor | medium | Open
DEFECT_12 | Order Tracking | Submit form with blank Email Address | Submit form with blank Email Address and it should indicate the error message towards Email address is missing | 1. Enter an valid order reference : XKBKNABJK 2. Leave Email Address blank 3. Click Send | Validation message indicates Email Address is required. | Error message displayed "Please provide the required information" | minor | medium | Open
DEFECT_13 | Order Tracking | Character limt in Order Reference input | In Order Tracking page there should be limitation of characters | 1. Enter more than 30 characters in Order Reference 2. Enter valid email 3. Click Send | Application should stop by 20characters as a maximum limit, if exeed error message should display | Character above 20 has excepted no error message displayed | minor | medium | Open
DEFECT_14 | Order Tracking | Verify browser refresh on Order Tracking page | After a Order Tracking page is open, eventhough we refresh the page it should remain with same info | 1. Refresh page 2. Verify fields and controls | Page reloads without errors and Order Tracking form remains functional. | Order page crashes and redirected to homepage | critical | high | Open
DEFECT_15 | Order Tracking | Verify the working of a Reorder Button inside a order | Checking the functionality of reorder button inside a valid order, for customer who wants to order the same item next time | 1, Look for Reorder Button. 2. Click on the Button | Should redirect to the shopping cart page and the item should display in Shopping cart | Redirected to Shopping cart but item is missing | major | high | Open
DEFECT_16 | Product Filters | Verify filter state after browser refresh | At least one filter is applied, after that user refresh page , page should remain same but it redirect to homepage | 1. Apply a filter 2. refresh the page | Page should remain in filtered page and the filer should be same | page changed to home page | major | high | Open

## Test Report
SL No | Features | Total Test cases | Number of defects
1 | Home Page | 22 | 3
2 | Product Description | 22 | 1
3 | Contact Us | 20 | 4
4 | Add to Cart | 26 | 2
5 | Checkout | 21 | 0
6 | Customer Login | 22 | 0
7 | New Customer Login | 23 | 1
8 | Order Tracking | 21 | 6
9 | Product Filters | 19 | 1
| Total | 196 | 18